## Sheet1
Milestones to Date | Description of Deliverables | Due Date | Completion Date | Comments
Iteration 1: Training | Training Phase
Twitter API Connection | Learn how to make API calls to Twitter | 2020-10-30 | 2020-10-25 | Learned to make API Call in NodeJS
MongoDB | Setup MongoDB cluster and learn to connect | 2020-10-30 | 2020-10-29 | Learned to make MongoDB cluster and connect to Mongo
VueJS/Vuexy | At least learn VueJS check Vuexy | 2020-10-30 | 2020-11-01 | Learned how to make a table and show it on a page using VueJS (Unfortunately did not get to Vuexy)
Heroku Deployment | Learn | 2020-10-30 | 2020-11-04 | Learn Heroku CLI for pushing changes to Heroku
Iteration 2: Actual App | Creating Actual App
API Calling | Make API Call using Twitter Endpoints | 2020-11-20 | 2020-11-16 | Make Call to Get Stream Endpoint to allow influx of information from Twitters API
MongoDB | Connect to mongoDB and put in info from twitter stream | 2020-11-20 | 2020-11-18 | Connect to MongoDB to have database show information
VueJS/Vuexy | Put into nice front end table to show information | 2020-11-20 | 2020-11-19 | Vuexy was unable to be finished because it just had too much to learn in a short amount of time and I wanted to focus on the main application and to get that working which did take longer than anticipated
Heroku Deployment | Deploy the Site on Heroku | 2020-11-20 | 2020-11-23 | Final Deployment was made November 23rd to have an actual live functioning site (I know this was later than completion, however other parts of the project began to pile up and I just had to finish)
Iteration 3: Stretch Goals |  | Stretch
Implement Search Query API Call |  | If Finished | N/A | Would love to finish this part of the project (my most wanted goal for this project) however it proved very difficult to figure this out (spent too much time trying to figure out how to do this)
User Authentication |  | If Finished | N/A | User Auth would have been done through Vuexy had I had the time I wanted to actually implement it to site, but after trying to figure out how to get everything to mesh together it was too much for the time scope
Other Media Sites |  | If Finished | N/A | This would be a far future idea, this would be super cool to tie into different platforms like Reddit, Facebook, Instagram, YouTube, etc.