## Project Planner
Twitter Analyzer Schedule
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Learning Tools | 1 | 8 | 1 | 8 | 100%
Twitter API Connect | 2 | 3 | 2 | 3 | 100%
Build Dashboard for Admin Backend | 2 | 4 | 2 | 5 | 50%
Build the Database | 4 | 8 | 4 | 6 | 100%
Get Data into Database | 4 | 2 | 4 | 8 | 100%
Let Dashboard Display Data | 4 | 3 | 4 | 6 | 75%
Milestone Review | 4 | 1 | 4 | 1 | 100%
System Test Procedure | 4 | 1 | 4 | 1 | 100%
Iteration 2 | 6 | 6 | 6 | 6 | 100%
Actual Build of Project | 8 | 3 | 0 | 0 | 0%
Twitter API Conect | 6 | 2 | 6 | 2 | 100%
Database creation/use | 7 | 1 | 8 | 2 | 100%
Basic dashboard table to display data | 8 | 2 | 9 | 3 | 100%
Show basic website with dashboard | 9 | 2 | 9 | 2 | 100%
Table into main dashboard | 10 | 3 | 11 | 3 | 60%
System Test Procedure | 12 | 2 | 13 | 2 | 90%
Deployment Test | 13 | 1 | 13 | 1 | 100%
Implementation of Stretch Goals | 14 | 2 | 14 | 0 | -
Final Presentation | 16 | 1 |  |  | 0%